## Summary
Version 5.11 |  | TECHNICAL ASSESSMENT
MSALFPO2_MisuiSumitomoAioiLife_Flax_PoC2_TA1
|  | Product | Flax | Project type | POC
|  | Risk Rate | #REF!
|  | Acc | Estimation | Duration (months) | 3
|  | Number of fields | 1 | Average target pages/ file | 1
|  | Acc by field | 80% | Required training data (file) | 600
|  | Acc by char | 80% | Required testing data (file) | 600
|  | Speed per page (fullflow including system) | #REF! | Total required data (file) | 1200
|  | Speed per page (AI flow) | #REF! | Total required data (target page) | 1200
|  | Work-days | #REF! | Tech Assessment Team
|  | Postion | Effort (Man day) | Name | Position | https://cinnamon-ai.atlassian.net/browse/TA-764
|  | DM Senior | #REF! | Satosy | DM | https://cinnamon-ai.atlassian.net/wiki/spaces/TA/pages/2576122763/MSALFPO2+MisuiSumitomoAioiLife+Flax+BRD
|  | DM Pre-Senior | #REF! | Ray | PM | https://cinnamon.slack.com/archives/CBG643NSF/p1669796209700109
|  | SE(JP) Senior/Pre-Senior | #REF! | Jason | AIR | Final Acc report of another project Sumitomolife https://cinnamon-ai.atlassian.net/wiki/spaces/GXCTG/pages/1745355810?atlOrigin=eyJpIjoiMmIzYjY1YmMyYzI4NDhhMWE5OWE0NDJiNDIwMmE2ZDMiLCJwIjoiY29uZmx1ZW5jZS1jaGF0cy1pbnQifQ
|  | AI(JP) Senior | #REF! |  | SE Backend
|  | PM Senior/Pre-Senior | #REF! | Jason | AIE
|  | AI Senior | #REF! |  | SE Frontend
|  | AI Pre-Senior | #REF! |  | UI/UX Designer
|  | AID Senior/Pre-Senior | #REF! |  | DevOps
|  | AID-JP Senior/Pre-Senior | #REF! |  | QAS
|  | SE Backend Senior | #REF! | Julie | QAL
|  | SE Backend Pre-Senior | #REF!
|  | SE Frontend Senior | #REF!
|  | SE Frontend Pre-Senior | #REF!
|  | UI/UX Designer Pre-Senior | #REF!
|  | SE DevSecOps Senior | #REF!
|  | SE DevSecOps Pre-senior | #REF!
|  | QAS Senior/Pre-Senior | #REF!
|  | QAL Senior/Pre-Senior | #REF!
| Group |  | Description |  | Mitigation
| Data |  | no real data -> this TA uses data of other projects (sumitomolife) Form MR/ME: Keyword of 2 field No.19/99 have never appeared in the previous projects with the same form
| AI module |  | no classification by AI which mean input data is classified by form type already. Other module, please refer AI sheet
| Human resource |  | high workload on both QAL (to label 1200 files) and AI (to cover 4 form type)
| System |  | n/a
| Report Schedule |  | 1st report - Week8 Final reprot - Week12

## PHASE1 WBS
Issue Type | Epic Name | Epic Link | Summary | Description | Reporter | Planned start (dd/mm/yyyy) | Planned End (dd/mm/yyyy) | Original Estimate (Hours) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Epic | Data Engineer Task |  | DE Development |  |  |  |  | #REF!
Task |  | DE Development | Crawling information of all apps | - Basic information: description, launched time, languages, price,… - Highlights infomation - Reviews: number of reivew, overall reviews, all comments |  |  |  | #REF! | Week 1: 10
Task |  | DE Development | Top, Recommend, Trend Apps in Homepage | - Popular - In the spotlight - Trending this month - Top free app |  |  |  | #REF! | Week 1: 8
Task |  | DE Development | Top search | Sorted by: - Best match - Most popular - Newest |  |  |  | #REF! | Week 1: 10
Task |  | DE Development | Crawling category Finding products | Subcategories: - Product sourcing (Tags: Finding suppliers, Dropshipping, Print on demand, Buying wholesale, Product sourcing-Other) |  |  |  | #REF! | Week 1: 5
Task |  | DE Development | Crawling category Selling products | Subcategories: - Selling methods(Retail, Mobile app builder, Online marketplaces, social media, live shopping, custome storefronts) - Product display(Product comparison, Quick view, 3D/AR/VR) - Product variants(Product options, Color swatches, Custom file upload) - Pricing(Competitive pricing, Custome pricing and quotes, whosale pricing, installments, payment providers) - Purchase options(Subscriptions, Pre-orders, Order limits) - Gifts(Gift cards, Gift receipts, Gift warpping) - Digital products(Digital downloads, Donations, Warranties and insurance, Appointment booking) - Blockchain(NFT distribution, Tokengating and loyathy) |  |  |  |  | Week 2: 8
Task |  | DE Development | Crawling category Order and shipping | SubCategories: - Managing orders(Order tagger, Order sync, Order editing, Merchant order notifications, Purchase orders, Invoices and receipts, Order and shipping reports) - Fulfilling orders(Order scanner, Warehouse management, Outsourced fulfillment, SKU and barcodes, Packing slips, Shipping labels, Shipping rate calculator, Packaging) - Managing inventory(Inventory sync, Product replenisment, stock alerts, Inventory optimization, Inventory tracking, Inventory forecastings) - Delivery and pickups (COD, Delivery date, In-store pickups, Local delivery) |  |  |  |  | Week 2: 8
Task |  | DE Development | Crawling category Store design | Subcategories: - Store pages(Page builder, Pre-lauch) - Navigation and search(Navigation and filters, search) - Images and media(Icons, Image slider, Image galleries, Image editor, Video editor, Audio player, Content manager) - Notifications(Product badges, Popups, Banners) - Store alerts(Countdown timer, Stock counter, Back in stock alert, Price change alert) - Internationalization(Currency, Language and translations) - Page enhancements(Event calendar, Store locator, Swasonal design,Accessibility, metafields) - Social proof(Social proof, Trust badges, Product reviews, visitor counter) |  |  |  |  | Week 2: 8
Task |  | DE Development | Crawling category Marketing and Conversion | Subcategories: - Search engine optimaztion(SEO, Page redirect, Sitemap builder, Speed optimization) - Advertising(Advertising, Retargeting ads, Social media ads, Affiliate programs, Product feeds) - Direct marketing(Offline marketing, Push notifications, SMS marketing) - Email marketing(Email marketing, Email capture, Campaign management) - Content marketing(Lookbookds, Blogs) - Promotions(Discounts, Gift with purchase, Giveaways and contests, Buy one, get one) - Upselling and cross-selling(Upselling and cross-selling, Product bundles, Recently viewed, Recommended products) - Cart modification(Cart modification, One-click checkout, Add to cart) - Cart recovery (Abandoned cart, Exit offers) |  |  |  |  | Week 3: 8
Task |  | DE Development | Crawling category Store managements | Subcategories: -Customer accounts(Accounts and login, Loyathy and rewardsa, Whishlists, Product registration, Gift registry) - Support(Chat, Phone support, Contact form, Feedback and surveys, FAQ, Customer order tracking, Returns and exchanges, Support ticket management) - Store data(Store data importers, Test data generator, Backup) - Operations(Collections manager, Bulk editor, Staff manager, Workflow automation, Enterprise resource planning) - Privacy and security (Fraud, Content protector, Age verifier, IP blocker, Legal, Privacy, Security) - Finances(Accounting, Taxes, Crowdfunding, Profit calculator, Financial reports) - Analytics(Sale analytics, Customer analytics, Daskboards, Store activity, Marketing analytics) |  |  |  |  | Week 3: 8
Task |  | DE Development | Get app data through API | TBA |  |  |  | #REF! | Week 3: 10
Epic | Set up the development environment |  | Set up the development environment |  |  |  |  | #REF!
Task |  | Set up the development environment | Setup database | NoSQL database |  |  |  | #REF! | Week 4: 3
Task |  | Set up the development environment | Setup schedule crawling everyday | Auto run all task in DE development |  |  |  | #REF! | Week 4: 5
Task |  | Set up the development environment | Setup crawling parallel | Multiprocess crawling |  |  |  | #REF! | Week 4: 5
Task |  | Set up the development environment | Develop API for querying database | API for: - Get query search with specific input - Get information of app |  |  |  |  | Week 4: 6
Task |  | Set up the development environment | Tracking update every day | [5 empty] | Week 4: 5
Task |  | Set up the development environment | Testing | bar: Week 4
Note on D1: ====== ID#AAAAPrjJa4g ADMIN (2021-09-21 09:19:07) Name of the Task
Note on E1: ====== ID#AAAAPrjJa4o ADMIN (2021-09-21 09:19:07) Output of the Task

## CAL SHEET
WORK RATE | 11$/hour
TOTAL WORK (HOURS) | 108
TOTAL COST FOR DEVELOPMENT ($) | 1188

## Automation (hidden)
DM | SE(JP) | AI(JP) | PM | AI | AID | AID-JP | SE Backend | SE Frontend | UI/UX Designer | SE DevSecOps | QAS | QAL
Senior | Senior/Pre-Senior | Senior | Senior/Pre-Senior | Senior | Senior/Pre-Senior | Senior/Pre-Senior | Senior | Senior | Pre-Senior | Senior | Senior/Pre-Senior | Senior/Pre-Senior
Pre-Senior |  |  |  | Pre-Senior |  |  | Pre-Senior | Pre-Senior |  | Pre-Senior